## Tabelle1
Project: Mugge (Mostly Unfinished Genre Grading Engine)

	Main Topic	Description	Status	Estimated Time	Completion Time	Aberrations	Editor
Sprint 1		First meeting and get together of the project members. Assignement of the Project Manager
5.5 - 27.5	Get used to the Topic	Find literature in the Internet, read papers, investigate solutions of others	done	1,5 weeks	1,5 weeks	A lot of possibilities and for the most of us new stuff to learn	All
	Define Goals	Define Goals from different point of views like academic, customer and project team	done	1 week	1 week		All
	Start with a coarse planning	Start with a first project plan and draw a picture about the different phases	done	0,5 week	0,5 week		All
	Finding a Data Set	Find a Data set of 10 different music genres and about 1000 samples about 30 seconds	done	2 days	2 days		Stella
Sprint 2		Reviewing Sprint 1 and discuss the Goals with Mr. Beckmann
27.5 – 4.6	Finish the planning	Come from the coarse grid to a fine grid and define the different steps of each part of our solution and distribut the steps to the group members	In Process	1 week			All
Sprint 3		Reviewing Sprint 2 and start working on the minimal viable product
4.6 - 12.6	Implement "MVP"	Implement an interface between preprocessing unit and feature module	Open	0,5 days			Claas
		Implement a class for one single audio format processing	Open	1 day			Claas
		Load audio files in wav format into Python with Librosa	Open	0,5 days			Florian, Claas
		understand STFT and FFT, which are needed for spectrograms	Open	1 day			Stella, Joshua, Dennis
		Get the Spectrogram of the audio data	Open	0,5 days			Stella, Joshua, Dennis
		Extract the MFCC-feature from spectrogram	Open	2 days			Stella, Joshua, Dennis
		Write the data in a file	Open	1 day			Stella, Joshua, Dennis
		understanding the mathematics of decision making given outcomes of several tests and find out what might be suitable for our case	Open	2 days			Florian
		Feed the network with training data	Open	1 day			Stella, Joshua, Dennis
		Build a first GUI and a first version of the overall architecture of the whole program	Open	1 day			Florian, Stella
Sprint 4		Reviewing Sprint 3
12.6 - 19.6	Add Feature "Zero Crossing Rate"	Implement an interface between preprocessing unit and feature module	Open	0,5 days			Claas
		Preevaluate differences of different audio preprocessings	Open	0,5 days			Claas
		Evaluate one NN regarding different input classes	Open	0,5 days			Claas
		Plot a waveplot to display the behaviour of the signal over time (seconds)	Open	1 day			Stella
		Plot a grid to display the number of times the signal changes value from positive to negative and vice versa during time. (The zero crossings)	Open	1 day			Stella
		Utilize Librosa to verify the result of the graph	Open	1 day			Stella
		Documentation of Feature "MFCC"	Open	4 days			Stella, Joshua, Dennis
Sprint 5		Reviewing Sprint 4
19.6 - 26.6	Add Feature "Spectral centroid"	Implement an interface between preprocessing unit and feature module	Open	0,5 days			Claas
		Evaluate the whole model concerning different input classes	Open	0,5 days			Claas
		Understand the meaning of spectral centroid for audio	Open	0,5 days			Joshua
		understand the mathematics of adverserial examples and decide for one algorithm to generate it	Open	1 day			Florian
		Implementation of the (1. and) 2. decision algorithm	Open	2 days			Florian
		Documentation of the main line of mathematical arguments underlying the decision	Open	2 days
		Extract the feature	Open	2 days			Joshua
		Write the data in a file	Open	1 day			Joshua
		normalize/scale the data	Open	1 day			Joshua
		Feed the network with training data	Open	2 days			Joshua
Sprint 6		Reviewing Sprint 5
26.6 - 3.7	Add Feature "Chords"	Implement an interface between preprocessing unit and feature module	Open	0,5 days			Claas
		Documentation of the audio and input documentation	Open	6 days			Claas
		Implementing the 3. decision algorithm	Open	0.5 - 1 day			Florian
		Implementing the 4. decision algorithm	Open	0.5 - 1 day			Florian
		Documentation of Feature "Zero Crossing Rate"	Open	6 days			Stella
		generating an adverserial example	Open	2 days			Florian
		Documentation of adverserial example	Open	1 day			Florian
		Divide input data into successive frames and transforme it to frequency domain	Open	0,5 day			Dennis
		Use Librosa to project the entire spectrum of the music data into 12 bins representing the 12 distinct semitones of the musical octave	Open	0,5 day			Dennis
		Extract the Chroma feature from the spectogram	Open	1 days			Dennis
		Extract feature vectors from the chroma vector	Open	1 day			Dennis
		Implement a chord recognition system	Open	2 days			Dennis
		Test and train the system	Open	2 days			Dennis
Sprint 7		Reviewing Sprint 6
3.7 - 10.7	Finish the Gui	Let the GUI look and work properly	Open	1 day			Florian
	Create the PPT	Create a PPT for the project presentation	Open	5 days			All
	Finish the documentation	Documentation of Feature "Chords"	Open	5 days			Dennis
		Unit all documentations	Open	1 day			All