## Tabelle1
Project: Mugge (Mostly Unfinished Genre Grading Engine)
| Main Topic | Description | Status | Estimated Time | Completion Time | Aberrations | Editor
Sprint 1 |  | First meeting and get together of the project members. Assignement of the Project Manager
5.5 - 27.5 | Get used to the Topic | Find literature in the Internet, read papers, investigate solutions of others | done | 1,5 weeks | 1,5 weeks | A lot of possibilities and for the most of us new stuff to learn | All
| Define Goals | Define Goals from different point of views like academic, customer and project team | done | 1 week | 1 week |  | All
| Start with a coarse planning | Start with a first project plan and draw a picture about the different phases | done | 0,5 week | 0,5 week |  | All
| Finding a Data Set | Find a Data set of 10 different music genres and about 1000 samples about 30 seconds | done | 2 days | 2 days |  | Stella
Sprint 2 |  | Reviewing Sprint 1 and discuss the Goals with Mr. Beckmann
27.5 - 3.6 | Finish the planning | Come from the coarse grid to a fine grid and define the different steps of each part of our solution and distribut the steps to the group members | In Process | 1 week |  |  | All
Sprint 3 |  | Reviewing Sprint 2 and start working on the minimal viable product
3.6 - 12.6 | Implement "MVP" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Implement a class for one single audio format processing | Open | 1 day |  |  | Claas
|  | Load audio files in wav format into Python with Librosa | Open | 0,5 days |  |  | Florian, Claas
|  | understand STFT and FFT, which are needed for spectrograms | Open | 1 day |  |  | Stella, Joshua, Dennis
|  | Get the Spectrogram of the audio data | Open | 0,5 days |  |  | Stella, Joshua, Dennis
|  | Extract the MFCC-feature from spectrogram | Open | 2 days |  |  | Stella, Joshua, Dennis
|  | Write the data in a file | Open | 1 day |  |  | Stella, Joshua, Dennis
|  | implement a neural network | Open | 2 days |  |  | Florian
|  | Feed the network with training data | Open | 1 day |  |  | Stella, Joshua, Dennis
|  | Build a first GUI | Open | 1 day |  |  | Florian
Sprint 4 |  | Reviewing Sprint 3
12.6 - 19.6 | Add Feature "Zero Crossing Rate" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Preevaluate differences of different audio preprocessings | Open | 0,5 days |  |  | Claas
|  | Evaluate one NN regarding different input classes | Open | 0,5 days |  |  | Claas
|  | Plot a waveplot to display the behaviour of the signal over time (seconds) | Open | 1 day |  |  | Stella
|  | Plot a grid to display the number of times the signal changes value from positive to negative and vice versa during time. (The zero crossings) | Open | 1 day |  |  | Stella
|  | Utilize Librosa to verify the result of the graph | Open | 1 day |  |  | Stella
|  | Parallelize the neural networks for each feature | Open | 2 days |  |  | Florian
|  | Documentation of Feature "MFCC" | Open | 4 days |  |  | Stella, Joshua, Dennis
Sprint 5 |  | Reviewing Sprint 4
19.6 - 26.6 | Add Feature "Spectral centroid" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Evaluate the whole model concerning different input classes | Open | 0,5 days |  |  | Claas
|  | Understand the meaning of spectral centroid for audio | Open | 0,5 days |  |  | Joshua
|  | Extract the feature | Open | 2 days |  |  | Joshua
|  | Write the data in a file | Open | 1 day |  |  | Joshua
|  | normalize/scale the data | Open | 1 day |  |  | Joshua
|  | Feed the network with training data | Open | 2 days |  |  | Joshua
Sprint 6 |  | Reviewing Sprint 5
26.6 - 3.7 | Add Feature "Chords" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Documentation of the audio and input documentation | Open | 6 days |  |  | Claas
|  | Documentation of the Neural Networks and the parallelization of them | Open | 6 days |  |  | Florian
|  | Documentation of Feature "Zero Crossing Rate" | Open | 6 days |  |  | Stella
|  | Documentation of Feature "Spectral centroid" | Open | 6 days |  |  | Florian
|  | Divide input data into successive frames and transforme it to frequency domain | Open | 0,5 day |  |  | Dennis
|  | Use Librosa to project the entire spectrum of the music data into 12 bins representing the 12 distinct semitones of the musical octave | Open | 0,5 day |  |  | Dennis
|  | Extract the Chroma feature from the spectogram | Open | 1 days |  |  | Dennis
|  | Extract feature vectors from the chroma vector | Open | 1 day |  |  | Dennis
|  | Implement a chord recognition system | Open | 2 days |  |  | Dennis
|  | Test and train the system | Open | 2 days |  |  | Dennis
Sprint 7 |  | Reviewing Sprint 6
3.7 - 10.7 | Finish the Gui | Let the GUI look and work properly | Open | 1 day |  |  | Florian
| Create the PPT | Create a PPT for the project presentation | Open | 5 days |  |  | All
| Finish the documentation | Documentation of Feature "Chords" | Open | 5 days |  |  | Dennis
|  | Unit all documentations | Open | 1 day |  |  | All