## Tabelle1
Project: Mugge (Mostly Unfinished Genre Grading Engine)
Spalte1 | Main Topic | Description | Status | Estimated Time | Completion Time | Aberrations | Editor
Sprint 1 |  | First meeting and get together of the project members. Assignement of the Project Manager
5.5 - 27.5 | Get used to the Topic | Find literature in the Internet, read papers, investigate solutions of others | done | 1,5 weeks | 90 hours | A lot of possibilities and for the most of us new stuff to learn | All
| Define Goals | Define Goals from different point of views like academic, customer and project team | done | 1 week | 1 week |  | All
| Start with a coarse planning | Start with a first project plan and draw a picture about the different phases | done | 0,5 week | 15 hours |  | All
| Finding a Data Set | Find a Data set of 10 different music genres and about 1000 samples about 30 seconds | done | 2 days | 8 hours |  | Stella
Sprint 2 |  | Reviewing Sprint 1 and discuss the Goals with Mr. Beckmann | Done | 1h | 1h |  | All
27.5 – 4.6 | Finish the planning | Come from the coarse grid to a fine grid and define the different steps of each part of our solution and distribut the steps to the group members | Done | 40 hours |  |  | All
Sprint 3 |  | Reviewing Sprint 2 and start working on the minimal viable product | Done | 1h | 1h |  | All
4.6 - 12.6 | Implement "MVP" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Implement a class for one single audio format processing | Open | 1 day |  |  | Claas
|  | Load audio files in wav format into Python with Librosa | Done | 0,5 days | 4h |  | Florian, Claas
|  | understand STFT and FFT, which are needed for spectrograms | Done | 1 day |  |  | Stella, Joshua, Dennis
|  | Get the Spectrogram of the audio data | Not needed | 0,5 days |  | (creating spectograms was not necessary for our feature extraction ) | Stella, Joshua, Dennis
|  | Extract the MFCC-feature from spectrogram | Done | 2 days | 4h | extracted the features directly from .wav file | Stella, Joshua, Dennis
|  | Write the data in a file (.csv) | Done | 1 day | 2h |  | Stella, Joshua, Dennis
|  | Read file, import data with pandas and normalize/scale the data | Done | 2h | 3h |  | Stella, Joshua, Dennis
|  | Implement a classifier and feed it with training data | Done | 1 day | 6h |  | Stella, Joshua, Dennis
|  | understanding the mathematics of decision making given outcomes of several tests and find out what might be suitable for our case | Done | 2 days |  |  | Florian
|  | Build a first GUI and a first version of the overall architecture of the whole program | Done | 1 day |  |  | Florian, Stella
Sprint 4 |  | Reviewing Sprint 3 | Done | 1h | 1,5 h |  | All
12.6 - 19.6 | Add Feature "Zero Crossing Rate" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Preevaluate differences of different audio preprocessings | Open | 0,5 days |  |  | Claas
|  | Evaluate one NN regarding different input classes | Open | 0,5 days |  |  | Claas
|  | Extracting zero crossing rate,mfccs and spectogram just for one audio file and visualize them to have a general idea of the features | Done | 2h | 3h |  | Stella
|  | Extract Spectrogram for all audio files of the dataset | Done | 2h | 5h |  | Stella
|  | Create a csv file, extract the features from the dataset and store the data into the csv file | Done | 3h | 16h |  | Stella
|  | Split the dataset into training and testing set | Done | 1h | 1h |  | Stella
|  | Apply ML algorithms and check the accuracy storing the results in confusion matrices | Open | 10h |  |  | Stella
|  | Documentation of Feature "MFCC" | Not needed | 20 h |  | Shifted into the last Sprint because we only need a Presentation | Stella, Joshua, Dennis
Sprint 5 |  | Reviewing Sprint 4 | Done | 1h | 1,5 h |  | All
19.6 - 26.6 | Add Feature "Spectral centroid" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Evaluate the whole model concerning different input classes | Open | 0,5 days |  |  | Claas
|  | Understand the meaning of spectral centroid for audio | Done | 0,5 days | 1h |  | Joshua
|  | implementation of main function | Done | 30 h |  |  | Florian
|  | Extract the feature | Done | 2 days |  |  | Joshua
|  | Write the data in a file | Done | 1 day |  |  | Joshua
|  | normalize/scale the data | Done | 1 day |  |  | Joshua
|  | Feed the network with training data | Done | 2 days |  |  | Joshua
|  | Implement several Classifiers and test them on our data set (with all features and only on single features) | Done |  | 8h |  | Joshua and Stella
|  | Compare the accuracies of those classifiers, using a barchart as visualization | Done |  | 5h |  | Joshua
Sprint 6 |  | Reviewing Sprint 5 | Done | 1h | 1h |  | All
26.6 - 5.7 | Add Feature "Chords" | Implement an interface between preprocessing unit and feature module | Open | 0,5 days |  |  | Claas
|  | Documentation of the audio and input documentation | Open | 6 days |  |  | Claas
|  | finish main function | open | 1 day = 10h
|  | Documentation of the main line of mathematical arguments underlying the decision | Not needed | 2 days |  | Shifted into the last Sprint because we only need a Presentation | Florian
|  | Implementing the decision algorithms | Open | 1 day = 10h |  |  | Florian
|  | Documentation of Feature "Zero Crossing Rate" | Not needed | 6 days |  | Shifted into the last Sprint because we only need a Presentation | Stella
|  | Extract a Pitch Class Profile Feature | Done | 5h | 4h | Probably using the Chroma Feature | Dennis
|  | Implement the Hidden Markov Model for the training phase | In Progress | 10 h |  | Core Elements are Trasition Prob. And observation distribution | Dennis
|  | Decode the chord sequence from the input audio | OPen | 5h |  | Maybe not needed. IF needed with maximum likelihood estimator | Dennis
|  | Incorporate the N-gram Model to the HMM framework | Open | 20 h |  |  | Dennis
|  | Testing the best N in the N-gram Model | Open | 2h |  | The paper got 3 as the best accuracy compared to workload | Dennis
|  | Test anmd train the system | Open | 8h |  |  | Dennis
|  | Play with parameters for the best accuracy with acceptable computation time | Open | 12h |  |  | Dennis
Sprint 7 |  | Reviewing Sprint 6
3.7 - 10.7 | Finish the Gui | Let the GUI look and work properly | Open | 2 days = 20h |  |  | Florian & Stella
|  | Implement graphics / visualizations for "box 7" of the GUI | Open | 6 hours |  |  | Joshua
| Create the PPT | Create a PPT for the project presentation | Open | 5 days |  |  | All
| Finish the documentation | Documentation of Feature "Chords" | Not needed | 5 days |  | Shifted into the PPT | Dennis
|  | Unit all documentations | Open | 1 day |  | Unit the PPTs | All